## Sheet1
# | Platform | Where | Comment | Done | Developer Comments | Web host Comments | links | final status
1 | Admin | Website pages | i can't manage the pages Contents like About , Contact, SM link ..etc |  | please send document screen shot where this point is mentiond | link printscreen
15 | Website | After purchse | how to change the message that shows after purchase, and a confirmation Email should be sent to the user |  | Thank you page is static page. Purchase detail email is now send to user | I test that, no email recived
44 | Website | Buy book or product | a bug at the end of the buying process showing the error code page link printscreen (see the link) |  | done | link printscreen link printscreen 2 | the end should show thank you html | not solved
47 | Website | all | how to change english to arabic - please share the string file if you have it see the link on right |  | string translation menu is added on sidebar. But first we have to translate all arabic content into english then we can adjust many things | file link on server template Example
48 | Website | all | all titles for bages are not mapped correctly "titles in top of pages" |  | kindly provide titles of all pages
49 | Website | Send form | Fix sending to "support@bettertrend.com" using SMTP "support@dnet.sa" Pass : BtBt@2020 Subject : Support message from: ($Name) Message : body Content (Name)(Message type)(Email)(Mobile)(Message content) |  | kindly provide host mail host and port as well and kindly check your given details . It is not working. And also check emails in spam folder
51 | Website | Media Video/Images/Documents | Make the tiltle above the video/image/document and don't show the words Tiltle & description Also (optional if you can do this quickly) make the decsription read hyperlinks automaticly please, and text alignment justify |  | Pending
52 | Website | Contact us for the user page | Subject list are in English, the should be in Arabic as the language set. and the list should be same as contact us on the top for non user I alos test it, no Email received to support@bettertrend.net |  | Translation issue
53 | Website | User page / events | when viewing event details, the event zoom link is not showing, no field in the table for the online link for online events, the integration with zoom should provide the link autmaticly to the event link field |  | Not Found
54 | Website | Home | Add a logout button next to the login button, for a user to logout. He needs to go inside his page to logout and that is not correct. Also a language selection is not shown |  | Done
55 | Website | Register | at the end of register new user, an error page is showing, no confirmation Email sent to the new user, although the user is registered as I can see in the admin page and user can login without problems, just fix the issue that is hapening at the end of registration process |  | Done
56 | Website | Events user page | Remove the registration form if the user loged in, this create confusion no need for purchase form Also, in the event detail page show the price of the event then, in the payment page, move the price of the event from the top to below the coupon field down check the link http://prntscr.com/p4e4r8 |  | Done |  | http://prntscr.com/p4e4r8
57 | Website | Events user page | the titles in the table of events looks not correct, please check the link http://prntscr.com/p4e8ak for explenation of the titles in Arabic |  | Translation issue |  | http://prntscr.com/p4e8ak
58 | Admin | Events | In the form to create or edit an event, no field to upload videos or attachments, Add video 1, description 1, attachment 1 then video 2, attachment 2, description 2... until 10, and arrange to have comments for each video |  | Will not done |  | http://prntscr.com/p4e8ak
59 | website & Admin | Events | Add video players (10 fields) to upload videos of the events which are the recording of the event and show those videos in the user events details page, also allow Comments & Attachment like those in the school videos no need to show the videos in the summary list of emails, just in the create/edit forms for the admin, and for the user, show those videos if the user click on the show details of the events, it should list all videos recordings then description of the video then attachment of the video then comments for the video, then video 2... until video 10. All videos in the same details page of the event |  | Will not done |  | http://prntscr.com/p4e8ak
60 | Admin | users | I can not track users traffic in the website, thier used IP addresses (log for users activities in the website) |  | Will not done
61 | Admin | Exams | Saving the Exam provide me with error page I can not add exams, although the added exam I see it in the test questions drop down menu, and because I added it more than one time, it shows more than that I added |  | Not Found | http://prntscr.com/p4el2c | http://prntscr.com/p4ejns
62 | Admin | Exams | After adding new exam and see the error page, I'm not able to open the exam page from the admin, maybe because there is more than exam with same name? |  | Not Found
63 | Admin | Test Questions | I can only see question images, no field to add the question for the image, so add field to put the question for the image? |  | Kehna kia chahtay ho
64 | Website | Schools/videos | No back link to previous up level from video to chapter and from chapter to school |  | Done
65 | Website | chapter test | If number of questions is only 1, the rating for the test is 10% not passed? so it is designed that number of question should be 10?? the exam not required to be 10 question it could be 1 or 100, please add a wieght for each question and the total is 100% and no need to be 10 question |  | Done
66 | Website | chapter test | Add back button to get back to previous question and if a question not answer why it take to long to go to next question? the user can leave the question unanswered if the question not answered, and the user click continue, the page still waiting for answer
67 | Website | test result page | After test result, it shows all tests trails, but no link to take the user back to list of videos |  | Done
68 | Website | Schools/cources | A link to take the user his tests results (make if he click the exam status)
69 | Website | online schools | new user can still see the option to enroll to a school and he is already enrolled, He can not see the same package again, yes. but he also should not be able to enroll to the same school. A user can have more than one package for multiple school, but one school can not be in more than one package Yes, he can not enroll as the drop down menue is not showing the school to choose it, but also enroll button from the begining should not be shown
70 | Website | Media Video/Images/Documents | All videos that I added before in my testing are gone?? this is the next time I noticed this? why my entries are removed
71 | Admin | Media Pages | Change the title on the top from youtube videos to Media Videos
72 | Website | Most of the pages | Some pages the client don't have a link to go back to previous page, or make it as the events pages where the title has the link to get back, see screenshot |  |  | http://prntscr.com/p4vbhm http://prntscr.com/p4vd63 | http://prntscr.com/p4val4
73 | Website | Packages (plans) | Title of the package is not showing only desciption, see the screenshot |  |  |  | http://prntscr.com/p4v8jf
74 | Admin | All Pages | I need you to add a dublicate button to clone entry, next to Edit, Delete, View actions
75 | Admin | String Translations | make the default view of entries 500 entries instead of 10 and allow the admin chooses to write the page number to jump to quickly. and make the number of entries up to 500 instead of 100 And if I edited any entry (or delete), please let the page tak me to the last edited page not all the way to the 1st page Allow the value of a string to be empty or space if I want it not to appear
76 | Website | My purchases in user page | No need for view details button, it shows nothing
77 | website & Admin | Packages link with schools and products | I don't feel comfortable with linking between packages and schools. A package (from its name) can have multiple schools if Admin allows it, so the user when goes to a package he should be able to choose which schools that he can enroll to (more than one if admin make them available). Admin specifies in creating the school plan Duration, number of schools that can be choosen, and other products also. Creating the school plan from admin should allow the admin to choose which schools are included in this package and how meny schools can the user enroll into and what products and how many that the user can choose. Currently for a user to enroll in two schools, for example, he has to purchase two packages which does not make sense. So when a user wants to enroll to a school, he click on it, then it shows to him which package he wants? then he chooses the package and click (check) the schools he wants, and check the products he wants. Once the user enrolled to a package, he can not then buy the same package again with the same school until it is expired, to void duplication buying same thing. He can buy another package even if it has the same school, no problem Example, a user purchase a Gold Package (1 month) this package has offer more than 1 school but the user can choose one of them only "Khalid School" it should open that package then show the user all schools available (just the name of the school with link to its page) and he can chooses only one, and all products available he can choose the number allowed. Later he can buy the Dimond Package (1 year) that has the same school with other schools and other products (upgrade) he chooses the number of schools allowed and number of products allowed. But he can't buy the Silver package (2weeks) with the same school because that is a downgrade. He can NOT purchase the same package Gold package with the same school Khalid. He can buy another Gold Package (1 month) with another School (Mohammed School). Look at the three packages that I created in school plans, you get the full idea of what I want